Practical No. 3

Aim: Estimate Project Cost using COCOMO Model

Introduction

COCOMO means Constructive Cost Model. Barry Boehm made it to estimate how much effort, time and people a software project needs from the size of the code. Size is usually written in KLOC (thousands of lines of code). From effort I can also get a rough project cost if I fix a cost per person-month.

My project is SeatAnything (Universal Seat Booking Platform) from Practical 1. Users search events, pick seats on a map, book and pay. Providers manage layouts and prices. The system needs login, real-time seat hold, payments, provider dashboard and notifications. In this practical I apply Basic and Intermediate COCOMO on my size estimate for version 1.0 and convert effort into cost.

COCOMO Overview

1. Basic COCOMO

Basic COCOMO uses only size and project mode. Effort in person-months (PM) is a × (KLOC)^b. Development time in months is c × (Effort)^d. Average staff is Effort divided by Time. Constants a, b, c, d change with the mode.

2. Intermediate COCOMO

Intermediate COCOMO still uses size, but multiplies effort by an Effort Adjustment Factor (EAF). EAF is the product of cost-driver ratings (product, computer, personnel, project). Effort = a × (KLOC)^b × EAF. Time formula stays the same form with intermediate constants. This is better when I already know something about team skill, reliability needs and tools.

3. Project modes

Organic mode is for small teams and familiar, flexible work. Semi-detached is for medium projects with mixed experience and some hard constraints. Embedded is for tight hardware, real-time or strict rules where change is costly. SeatAnything is a web SaaS with payments, concurrency and third-party APIs, but not firmware. I treat it as semi-detached.

Size Estimate for SeatAnything

I do not have finished source yet, so KLOC is a planning estimate from the SRS feature list. I count new application code for version 1.0 (backend APIs, web UI, booking engine, provider tools). I leave out pure config and third-party libraries.

| Module (from SRS) | Approx. KLOC | Why this size |
| --- | --- | --- |
| Auth, profile, SSO hooks | 3.0 | Login, sessions, user profile, basic MFA path for providers |
| Search and listing | 2.5 | Filters, results, event/service catalog APIs |
| Interactive seat map + hold timer | 6.0 | Real-time map, multi-seat select, 10-min hold — hardest core |
| Booking, cancel, history | 3.5 | Reservation lifecycle and user booking views |
| Payments (Stripe/PayPal integration) | 3.0 | Checkout, webhooks, failure/refund paths |
| Provider dashboard (layout, pricing) | 5.0 | Drag-drop layout editor and tier pricing |
| Notifications (email/push) | 2.0 | Confirmations, reminders, status mail |
| Admin, security hardening, NFR work | 2.5 | Rate limits, backups hooks, audit-ish admin |
| Tests and integration glue (counted half) | 2.5 | API tests, booking race tests, payment sandbox |
| Total estimated size (KLOC) | 30.0 | Version 1.0 planning figure |

So I take KLOC = 30 for the calculations below. If the seat map or provider editor grows, size can move toward 35–40 KLOC; if we cut medium-priority polish, it can fall near 22–25 KLOC. I keep 30 as the middle case.

Basic COCOMO Calculation

Mode: Semi-detached. Constants: a = 3.0, b = 1.12, c = 2.5, d = 0.35.

Effort E = 3.0 × (30)^1.12. First 30^1.12. 30^1 = 30 and 30^0.12 ≈ 1.51 (because 30^0.1 ≈ 1.43 and a bit more for 0.02), so 30^1.12 ≈ 45.3. Then E ≈ 3.0 × 45.3 ≈ 135.9 person-months. I round to about 136 PM.

Time T = 2.5 × (136)^0.35. 136^0.35 is roughly 5.0 (check: 136^0.3 ≈ 4.3 and 136^0.05 ≈ 1.16, product ≈ 5.0). T ≈ 2.5 × 5.0 ≈ 12.5 months.

Average people P = E / T ≈ 136 / 12.5 ≈ 10.9, so about 11 people if the schedule is packed that way. For a college or small startup team this is high; it means either a longer calendar with fewer people, or a cut in scope. COCOMO is giving the industrial-scale effort for this size, not a two-student lab roster.

| Quantity | Formula / note | Value |
| --- | --- | --- |
| Size (KLOC) | From module table | 30 |
| Mode | Chosen for SeatAnything | Semi-detached |
| Effort E (PM) | 3.0 × (30)^1.12 | ≈ 136 PM |
| Time T (months) | 2.5 × (E)^0.35 | ≈ 12.5 months |
| Avg. staff P | E / T | ≈ 11 people |

Intermediate COCOMO (with EAF)

Intermediate semi-detached constants use a = 3.0, b = 1.12 for effort before EAF (same size exponent family as basic for this mode in the simple class form we use in lab). I rate a few cost drivers that matter for SeatAnything. Ratings are relative to nominal = 1.00.

| Cost driver | My rating reason | Multiplier |
| --- | --- | --- |
| Required software reliability (RELY) | Booking and payment errors are costly; high but not life-critical | 1.15 |
| Product complexity (CPLX) | Real-time seats, concurrency, multi-tenant providers | 1.15 |
| Time constraint (TIME) | SRS wants fast booking (<200 ms class target); some pressure | 1.11 |
| Analyst capability (ACAP) | Small team, mixed experience — nominal/low | 1.00 |
| Programmer capability (PCAP) | Same team assumption | 1.00 |
| Application experience (AEXP) | First build of this domain for us | 1.13 |
| Use of software tools (TOOL) | Modern stack (cloud, good IDEs) helps a bit | 0.91 |
| Required development schedule (SCED) | Want v1 in about one year — slight stretch vs nominal | 1.04 |
| EAF (product of above) | 1.15×1.15×1.11×1.00×1.00×1.13×0.91×1.04 | ≈ 1.56 |

Effort_intermediate ≈ 3.0 × (30)^1.12 × 1.56 ≈ 136 × 1.56 ≈ 212 PM. Time with T = 2.5 × (212)^0.35: 212^0.35 ≈ 5.6, so T ≈ 2.5 × 5.6 ≈ 14 months. Average staff ≈ 212 / 14 ≈ 15 people. Reliability and complexity push effort up; tools pull a little down. Net EAF above 1 means Intermediate says Basic was optimistic for this product.

Cost Estimate

COCOMO gives effort, not money. Cost ≈ Effort × cost per person-month. I use a simple loaded cost for one developer in India for planning: ₹80,000 per person-month (salary plus rough overhead). Real companies differ a lot; this is only for the practical.

Basic COCOMO cost ≈ 136 × 80,000 = ₹1,08,80,000 (about ₹1.09 crore).

Intermediate COCOMO cost ≈ 212 × 80,000 = ₹1,69,60,000 (about ₹1.70 crore).

These numbers are for a full commercial v1 at 30 KLOC with a proper team. For a college build I would shrink scope (fewer provider tools, one payment gateway, simpler map) to maybe 12–15 KLOC and accept a longer calendar with 2–4 people. The model still shows why seat locking and payments are expensive: they raise both KLOC and EAF.

| Model | Effort (PM) | Time (months) | Cost @ ₹80,000/PM |
| --- | --- | --- | --- |
| Basic (semi-detached) | ≈ 136 | ≈ 12.5 | ≈ ₹1.09 crore |
| Intermediate (EAF≈1.56) | ≈ 212 | ≈ 14 | ≈ ₹1.70 crore |

Discussion

I chose semi-detached because SeatAnything is bigger than a simple student CRUD app, has external APIs and tough concurrency, but is still a normal cloud web system. Organic would understate risk. Embedded would overstate like safety-critical firmware.

Size is the weakest input. If KLOC is wrong, effort moves almost linearly-plus because of the exponent b > 1. My module table is honest guesswork from the SRS, not measured SLOC. After a few sprints I should re-estimate from real repos.

Intermediate EAF is also judgment. I pushed RELY and CPLX up because double-booking and payment bugs hurt trust. TOOL slightly down because modern frameworks help. Different raters would get different EAFs; that is normal for this model.

Schedule from COCOMO is the nominal development duration, not a promise. Adding people past a point does not cut time the same way (Brooks). For my Agile plan from Practical 2 I would use COCOMO as a budget ceiling, then plan increments inside a smaller MVP size.

Conclusion

For SeatAnything v1 I estimated 30 KLOC and used semi-detached COCOMO. Basic model gives about 136 person-months, 12.5 months and roughly 11 people, with cost near ₹1.09 crore at ₹80,000 per PM. Intermediate drivers for reliability, complexity and green domain experience raise EAF to about 1.56, so effort about 212 PM, time about 14 months and cost near ₹1.70 crore.

COCOMO is useful to see that a full seat-booking SaaS is not a tiny project. For class delivery I would cut scope and re-run the same formulas on a smaller KLOC. The method stays: size → mode → effort/time → cost, then Intermediate when I can rate cost drivers.